# OPOPPR Migration Analysis: JSF to React/Spring Boot

Document Information - Date: December 2024 - Version: 1.0 - Purpose: Analysis and estimation for migrating OPOPPR from JSF/Jakarta EE to React SPA with Spring Boot REST services

## 1. Executive Summary

This document provides a comprehensive analysis of migrating the Orleans Parish Online Personal Property Reporting (OPOPPR) system from its current JSF/PrimeFaces/Jakarta EE architecture to a modern React SPA with Spring Boot REST API backend.

Key Findings: - Estimated Timeline: 4-6 months - Team Size: 2-3 experienced developers
- Risk Level: Medium to High - Total Frontend Components: ~30 components across 7 categories

## 2. Current System Analysis

### 2.1 Technology Stack

- Frontend: JavaServer Faces (JSF) 2.0, PrimeFaces 5.3, XHTML templates

- Backend: Jakarta EE 7, JPA/Hibernate, CDI

- Database: MySQL 8.0 on AWS RDS Aurora

- Server: Apache Tomcat 9 on JDK 17

- Deployment: Docker containers on AWS Elastic Beanstalk

- Reports: Jasper Reports integration

### 2.2 System Complexity Metrics

- Pages: ~15-20 JSF pages with complex templating

- Controllers: ~25 JPA controller classes

- Entities: ~10 database entities with complex relationships

- Features: Multi-step wizard forms, file upload/processing, report generation, admin functions

## 3. Migration Strategy

### 3.1 Four-Phase Approach

Phase 1: Backend API Development (6-8 weeks) - Set up Spring Boot project structure - Convert JPA entities and create DTOs - Implement REST controllers for all CRUD operations - Migrate authentication to JWT/Spring Security - Convert file processing logic - Set up database migration scripts - Unit testing for APIs

Phase 2: Frontend Development (6-8 weeks) - Set up React project with routing - Create reusable UI components - Implement multi-step form wizard - Build admin dashboard - Integrate with REST APIs - Implement state management (Redux/Context) - Handle file uploads and downloads

Phase 3: Integration & Testing (3-4 weeks) - End-to-end testing - Performance optimization - Security testing - Report generation integration - Docker containerization updates - AWS deployment configuration

Phase 4: Migration & Deployment (1-2 weeks) - Database migration scripts - Production deployment - User acceptance testing - Documentation updates

## 4. Detailed UI Component Analysis

### 4.1 Authentication & Session Management

Duration: 1-2 weeks

| Component | Source File | Effort | Description |
| --- | --- | --- | --- |
| Login Form | login.xhtml | 2-3 days | Account/PIN validation, error handling |
| Session Management | N/A | 3-4 days | JWT tokens, route guards, auto-logout |

### 4.2 Dashboard Components

Duration: 1 week

| Component | Source File | Effort | Description |
| --- | --- | --- | --- |
| Home Dashboard | home.xhtml | 3-4 days | Form status cards, timestamps, navigation |
| Admin Dashboard | homeAdmin.xhtml | 2-3 days | Admin action buttons, status widgets |

### 4.3 Multi-Step Form Wizard

Duration: 3-4 weeks

| Component | Source File | Effort | Description |
| --- | --- | --- | --- |
| Master Template | masterTemplate.xhtml | 3-4 days | Layout, breadcrumbs, progress indicator |
| Form Header | header.xhtml | 2-3 days | Business info fields, contact details |
| Section 1 | section1.xhtml | 2-3 days | Form validation, dynamic interactions |
| Section 2 | section2.xhtml | 2-3 days | Form validation, dynamic interactions |
| Section 3 | section3.xhtml | 2-3 days | Form validation, dynamic interactions |
| Section 4 | section4.xhtml | 2-3 days | Form validation, dynamic interactions |
| Section 5 | section5.xhtml | 2-3 days | Form validation, dynamic interactions |
| Form Validation | validate.xhtml | 3-4 days | Cross-section validation, error display |

### 4.4 Data Entry Components

Duration: 2-3 weeks

| Component | Source File | Effort | Description |
| --- | --- | --- | --- |
| Property Asset Tables | Multiple | 4-5 days | Editable grids, add/remove rows, validation |
| Inventory Management | Multiple | 3-4 days | Dynamic lists, calculation logic |
| Filing Information | Multiple | 2-3 days | Document upload, file validation |

### 4.5 Administrative Features

Duration: 2-3 weeks

| Component | Source File | Effort | Description |
| --- | --- | --- | --- |
| Database Management | initialize.xhtml, close.xhtml | 3-4 days | CSV imports, progress indicators |
| Export Functionality | export.xhtml | 2-3 days | Data export forms, file downloads |
| Form Status Management | resetFormStatus.xhtml | 2-3 days | Form selection, bulk operations |
| Report Generation | lat5StatusReport.xhtml | 4-5 days | Report parameters, PDF integration |

### 4.6 Common UI Components

Duration: 1-2 weeks

| Component | Source File | Effort | Description |
| --- | --- | --- | --- |
| Navigation Components | Multiple | 2-3 days | Menu, breadcrumbs, user dropdown |
| Form Controls Library | Multiple | 3-4 days | Custom inputs, validation, loading states |
| Modal Dialogs | Multiple | 2-3 days | Confirmations, messages, help overlays |
| Data Tables | Multiple | 3-4 days | Sortable/filterable, pagination, selection |

### 4.7 Responsive Design & Styling

Duration: 1-2 weeks

| Component | Source File | Effort | Description |
| --- | --- | --- | --- |
| CSS Framework Setup | opoppr.css | 2-3 days | Theme configuration, component styling |
| Mobile Responsiveness | Multiple | 3-4 days | Form layouts, navigation adaptations |
| Accessibility Features | Multiple | 2-3 days | ARIA labels, keyboard nav, screen readers |

## 5. Time Estimation Summary

| Category | Components | Duration |
| --- | --- | --- |
| Authentication | 2 components | 1-2 weeks |
| Dashboards | 2 components | 1 week |
| Form Wizard | 8 components | 3-4 weeks |
| Data Entry | 3 components | 2-3 weeks |
| Admin Features | 4 components | 2-3 weeks |
| Common Components | 4 components | 1-2 weeks |
| Styling & UX | 3 areas | 1-2 weeks |
| TOTAL FRONTEND | 26 components | 11-17 weeks |

## 6. Risk Analysis & Mitigation

### 6.1 High Risk Areas

| Risk | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| Complex Form Validation Logic | +2-4 weeks | High | Early prototyping, rule documentation |
| File Processing & CSV Import | +1-2 weeks | Medium | Maintain shell scripts, REST wrapper |
| Report Generation Integration | +1-2 weeks | Medium | Modern reporting alternatives |
| Undocumented Business Logic | +2-4 weeks | High | Code reviews, stakeholder interviews |

### 6.2 Medium Risk Areas

| Risk | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| Session State Management | +1 week | Medium | Redux/Context implementation |
| Database Migration | +1 week | Medium | Parallel system operation |
| Performance Optimization | +1-2 weeks | Medium | Load testing, query optimization |

## 7. Technology Recommendations

### 7.1 Frontend Technology Stack

- Framework: React 18+ with TypeScript

- UI Library: Material-UI or Ant Design

- State Management: Redux Toolkit or Zustand

- Routing: React Router v6

- Forms: React Hook Form with Yup validation

- HTTP Client: Axios with interceptors

### 7.2 Backend Technology Stack

- Framework: Spring Boot 3.x

- Security: Spring Security with JWT

- Data: Spring Data JPA with MySQL

- Documentation: OpenAPI 3.0 (Swagger)

- Testing: JUnit 5, TestContainers

- Build: Maven or Gradle

## 8. Success Criteria

### 8.1 Functional Requirements

✓ All existing functionality preserved
✓ Improved user experience and performance
✓ Mobile-responsive design
✓ Accessibility compliance (WCAG 2.1)

### 8.2 Technical Requirements

✓ RESTful API design
✓ Comprehensive test coverage (>80%)
✓ Performance metrics maintained or improved
✓ Security standards met or exceeded
✓ Deployment automation

### 8.3 Business Requirements

✓ Zero data loss during migration
✓ Minimal downtime during transition
✓ User training materials updated
✓ System documentation complete

## 9. Conclusion

The migration from JSF/Jakarta EE to React/Spring Boot represents a significant modernization effort that will improve the OPOPPR system’s maintainability, user experience, and alignment with current web development standards.

Key Success Factors: - Early identification and documentation of business logic - Incremental development with regular stakeholder feedback
- Comprehensive testing throughout the development process - Parallel system operation during transition period - Adequate buffer time for unforeseen complexity

The estimated 4-6 month timeline is achievable with proper planning, experienced developers, and committed stakeholder support. The resulting system will provide a solid foundation for future enhancements and maintenance.